## Sheet2
02/28/11
HOMEPAGE	Notes
Done*	Will swap with new JS Component	D: Change arrow bars on top scroll.
Done*	Will swap with JS Componentn from Verisisng	D: Design SSL/Verisign protection design.
?	Didn't see on comp	- Email, username and password information
?	Didn't see on comp	- Subscriptions.
		- Skin of “My Account” – stage.constellation.tv/account
Done	This is now a 24 hour list, do you want to do now to midnight?	C: Make UP NEXT a static scroll bar, not an active scroll. “UP NEXT” means, literally, what is showing next. A user should be able to scroll down as far as there are screenings scheduled for the current day.
		Featured screenings currently static

FILM PAGE
Done*	Set it to width of column, 205 x 141	D: Redo the image size of the featured screening that is up next to be 360 by 246.
		C: The reviews at the top should automatically scroll. They should be links that take the user to the articles that the text is pulled from.
		D: Make “Future Showtimes” same font as what is used for the top right “My Account” module link.

		Need to write “FREE TICKET” popups
		Buzz needs to be film specific
		Featured screenings currently static

POPUPS
?	Couldn't Reproduce	C: The text at top of most of the popups is getting cut off at the top. Clipping.
	Need MM Account Info	C: Purchase popup, integrate MaxMind, Fraud Protection. Block IP service, above some reasonable threshold.
??	Growlers, no?	D: Failed data entry positions for messages.

ERROR/NOTICE Form
		- Notice that screening just started.
??	No such thing! Just have a new screening instance...	§ Sold Out
??	This isn't an error or notice, shouldn't it be a popup?	o Confirmation
??	This isn't an error or notice, shouldn't it be a popup?	§ Ticket was purchased

LOBBY
		- You have been blocked from this screening by the system administrator.

ADMIN
		- C: Need to include metrics per film before Beta Launch.
		Need to add chargebacks and voids to payment admin

THEATER		-

		- C: Mapping Constellation in theater.
		- C: Make menu popups opaque.
		- D: button for host to end Q+A.
		- Need to add ability for admins to get into any screening without bnuying a ticket.
??		- Need to add “Surender Your Seat” message to come up and then fade away when user enters the theater.
??		- Need to redesign overlays:
		o Propmotion popup.
		o Q+A interface design
		o The screening is now over.
		- C: Add the promotion start time to the film admin (incl;uding negative time).
		- D: Redo theater background to eliminate stars.
		- D: do a JPEG of the chat and the Q+A with chat box on top.
		QandA Testing