## Global Schedule
Item	Logged	Date Due	Completed Tech Description	Notes
1. Login/User Identification (Persistent)
1.0 Constellation custom login		18-Dec	Done	Do not require splash page
1.1 User uses email, a login name and password to create an account		18-Dec	Done using PHP/JS	Create new FB, TW APIs, put in docs folder
1.1.1. User logs in to Facebook (Saved Locally)		18-Dec	Done with Oauth Classes Serverside
1.1.2. User logs in to Twitter (Saved Locally)		18-Dec	Done with Oauth Classes Serverside
1.2 Upcoming Screenings			Done
2. Static Content (Persistent)
2.0 Contact
2.1 Terms of Service
2.2 Privacy Policy
2.3 Purchase Policy
2.4 How It Works
2.5 FAQ's
2.6 About Us
2.7 Want To Host A Screening (TBD)
3. Sharing (Persistent)
3.0 Twitter (Constellation Home)
3.1 Facebook (Constellation Home)
4. Homepage
4.0 Featured Showtimes All Films		20-Dec	Done, PHP and SOLR
4.0.1. Join Link		20-Dec	Done, PHP and SOLR
4.0.2. Show Information (iCal format)		20-Dec	Done minus iCal
4.0.3. Expandable Rollover (TBD)		20-Dec	TBD
4.1 Poster Carousel		20-Dec	Done, via SOLR and AJAX
5. Film Specific
5.0 Trailer		21-Dec	Done
5.1 Reviews		22-Dec	Done, PHP and SOLR	*currently, reviews are getting cut off; need to make click
5.2 Film Details		21-Dec	Done, PHP and SOLR
5.3 Screening Schedule		22-Dec	Done, PHP and SOLR
5.3.1. Join Link		22-Dec	Done, PHP and SOLR
5.3.2. Showtime Information		22-Dec	Done, PHP and SOLR
5.3.2.1. Calendar With Further Showtimes		22-Dec	Done	Expanded Calendar with other days, clicking on day populates “Other Showtimes”
5.3.2.2. Expandable Rollover (TBD)		22-Dec	TBD
6. Purchase Tickets
6.0 Trailer		21-Dec	Done
6.1 Screening Schedule (Inherit from 5.3)		22-Dec	Done, PHP and SOLR
6.1.1. Join Link		22-Dec	Done, PHP and SOLR
6.1.2. Showtime Information		22-Dec	Done, PHP and SOLR
6.1.2.1. Calendar With Further Showtimes		22-Dec	Done, PHP and SOLR
6.1.2.2. Expandable Rollover (TBD)		22-Dec	TBD
6.2 Activity Report (From 6.0 and 7.0)		3-Jan	Done, still enumerating instances.	Activity: User enters theater, user enters chat comment, user posts review, user invites X number of friends, user
6.3 Screening Information		6-Jan	Done
6.4 Purchase Process		6-Jan
6.4.1. Join/Login		3-Jan	Done
6.4.3. Promotion Presentation (TBD)		3-Jan	In Process	*controlable from backend	Invite 10 get a free ticket
6.4.4. Invite Friends (Inverted from Current)		4-Jan	Done
6.4.3. Promotion Redemption (TBD)		3-Jan	In Process	*controlable from backend	Get your free ticket
6.4.5. Buy A Ticket		4-Jan	Done
6.4.5.1. Credit Card		4-Jan	Done
6.4.5.2. Paypal		4-Jan	Done
6.4.5.3. Redeem Subscription		5-Jan	Done	*one per email
6.4.5.4. Gifting Tickets		5-Jan	Done
6.4.6. Enter The Theater		22-Dec	Done	*Create unique access urls
6.4.7. Ticket Notification		13-Jan	Done
6.5 Ticket Exchange		5-Jan	Done
6.6 Countdown		3-Jan	Done, need actual start time
6.7 Toasters		5-Jan
6.7.1. Screening Started		5-Jan
6.7.2. Screening Completed		5-Jan
6.7.3. Screening Sold Out		5-Jan
6.7.4. Etc...		5-Jan
6.8 Timezone Set		6-Jan
10. Host A Screening		22-Dec	Done	Authentication for unique viewer
10.0 Trailer		21-Dec	Done
10.1 Screening Schedule (Inherit from 5.3)		22-Dec	Done, PHP and SOLR
10.1.1. Join Link		22-Dec	Done, PHP and SOLR
10.1.2. Showtime Information		22-Dec	Done, PHP and SOLR
10.1.2.1. Calendar With Further Showtimes		22-Dec	Done, PHP and SOLR
10.1.2.2. Expandable Rollover (TBD)		22-Dec	TBD
10.3 Screening Information		6-Jan
10.4 Purchase Process		6-Jan
10.4.1. Join/Login		3-Jan	Done
6.4.2. Host A Screening		3-Jan	Done
10.4.2.1. Upload Picture		3-Jan	Done
10.4.2.2. Pick Date and Time		3-Jan	Done
10.4.2.3. Featured, Public, or Private		3-Jan	Done
10.4.5.1. Credit Card		4-Jan	Done
10.4.5.2. Paypal		4-Jan	Done
10.4.3. Promotion Presentation (TBD)		3-Jan	In Process	*controlable from backend
10.4.4. Invite Friends (Inverted from Current)		4-Jan	Done
10.4.6. Enter The Theater		22-Dec	Done	*Create unique access urls
10.8 Timezone Set		6-Jan
7. Screening Room		22-Dec	Done	Authentication for unique viewer
7.0 Prescreening Overlay				Content timing
7.0.1. Invitation Link		23-Dec	Done
7.0.2. Share Showtimes		23-Dec	Done
7.0.3. Theater How-To		23-Dec	Done
7.0.4. Screening Information		23-Dec	Done
7.1 Menu Bar		27-Dec	Done (Needs skinning)
7.1.1. Constellation Overlay		27-Dec	Done (Needs ordered star placement, and Star Removal)
7.1.1.1. Use Avatars as opposed to dots		27-Dec	TBD – (Simple Change)
7.1.1.2. Direct Chat		27-Dec	Done
7.1.1.3. Direct Chat Interrupts		27-Dec	Done
7.1.2. Chat		17-Dec	Done	Python server with Mongo DB backend; sortable by screening, user, text record. Combobox userselection
7.1.3. Film Information		23-Dec	Done
7.1.4. Q&A		23-Dec	Done	Need discussion with JL prior to build	If hosted, after Screening, show this full screen
7.1.4.1. Video Feed		28-Dec	Not Done, need Video Player
7.1.4.2. Question Input		28-Dec	Done
7.1.4.3. Host Question Selection		28-Dec	Done
7.1.4.4. Host Answer Input		28-Dec	Done
7.1.5. Help		23-Dec	Done
7.1.6. Watching Now (User Count)		23-Dec	Done
7.1.7. Review and Recommendations		27-Dec	Done	Content timing
7.1.8. Facebook Screening Share (Purchase)
7.1.9. Twitter Screening Share (Purchase)
7.1.10. Menubar Toggle		23-Dec	Done
7.2 Film Screenings		15-Jan	Done, adding eTokens	Content timing
7.3 Countdown		23-Dec	Done
7.4 Review and Recommendations Overlay		27-Dec	Done	Content timing	1.5 Minutes Prior to End
7.4.1. Stuff...			Done
7.5 Post Film Interview Overlay		29-Dec	Done, need HTML	Content timing
7.5.1. Fullscreen Overlay		29-Dec	Not Done, need Video Player
7.5.2. Questions Slideshow		29-Dec	Done
7.6 Promotions/Advertisements		30-Dec	Done
7.6.1. Concessions		30-Dec	Done?	How are these different from Banners/Promos?
7.6.2. Banners/Promos		30-Dec	Done
7.7 Host Remittance
7.7.1. Enter Paypal/Bank/CC Account Info for Remittance (TBD)
7.8 Security Restriction		13-Jan	Done
8. Subscriptions		7-Jan	Done	*Modal, login or join, X number of tickets for $X/month, radio select,
8.0 Login		7-Jan	Done	Just like payment page, but with subscriptions
8.1 Define Subscription		7-Jan	Done
8.1.1. X Tickets		7-Jan	Done
8.1.2. Timeperiod		7-Jan	Done
8.2 Payment Information		7-Jan	Done
8.2.1. Credit Card		7-Jan	Done
8.2.2. Paypal		7-Jan	Done
8.3 Auto Re-Subscribe		7-Jan	Can't do, thanks to PCI Compliance	We could potentially do this with paypal tho...
9. Account Management Page
9.0 Your Username/Password	20-Jan	24-Jan
9.1 Your Facebook Information	20-Jan	24-Jan
9.2 Your Twitter Information	20-Jan	24-Jan
9.3 Your Purchase History	20-Jan	24-Jan
9.4 Your Showtimes	20-Jan	24-Jan
9.5 Your Input	20-Jan	24-Jan
9.5.1. Questions	20-Jan	24-Jan
9.5.2. Reviews	20-Jan	24-Jan
9.5.3. IM	20-Jan	24-Jan
9.6 Your Subscriptions	20-Jan	24-Jan

10. Video Streaming
10.0 SSH access to Akamai working			Done
10.1 R-sync movie assets from S3 to Akamai	20-Jan	20-Jan	Done
10.2 Create E-tokenable storage bucket on Akamai for OnDemand streams	20-Jan	20-Jan	Done
10.3 Show E-tokening working for both On Demand and live streams via Akamai	20-Jan	20-Jan	In Process
10.4 Demonstrate the player in screening room playing an On-Demand stream and a live stream at a scheduled time	20-Jan	20-Jan

11. Screening Room - To Do
11.1 Host Webcam Feed (on both host and user views of the screening room)	20-Jan	23-Jan	In Process
11.2 Access Procedures/Permissions (see Enhancements and Modifications)	20-Jan	21-Jan

12. MISCELLANEOUS
12.1 Send JL email with full list of pages and states for site for design work	20-Jan	20-Jan	Done

Site Enhancements		See Sheet 2

Bugs		See Sheet 3

## Enhancements and  Modifications
Hosting Page:	Logged	Due Date	Status
Show upcoming screenings: 10 Max, with Time of 7 Days			Done
Add Calendar Clicker which updates column list on date click	20-Jan	20-Jan	Done
Add Destination URL to LoginOpts Component			Done
Carousel blowup image cut off on left (1st Image)			Done
Make Film Detail URL use Title			In Progress

Film Specific Page
Reformat for new Component Model			Done
Update and add Login JS to the Film Specific Page			Done
Make Activity come from ANY active Screening, behavior like Screening Page	20-Jan	21-Jan	In Progress
Maximum Comments 20, fade out old (Also for Purchase Page)	20-Jan	21-Jan	Done
Mix Activity and Comments in "Recent Activity" (Also for Purchase Page)	20-Jan	21-Jan	Done
Make All stuff in Left Column go to the Screening Page			Done

Subscription
(If logged in, go to "detail" not "purchase")			Done
Remove Invite Friends			Done
Make all "subscription" tickets have the same code			Done
Make all gift" tickets have different codes			Done

Account Area
Allow for changing of the subscription ticket codes

Overall
Limit Date Selection to future dates			Done
Upload component needs css color for text, and needs better messaging			Done
Add Host Message to Hosting Form with 200 Char limit			Done

Fix Host Image in Film Right Column			Not sure what goes there, but not a Host

Calendar
Need the upcoming screenings Calendar working on Details and Purchase pages.	20-Jan	21-Jan

Screening Room Access
Authentication Levels: need to set cookies to manage proper authentication procedures	20-Jan	21-Jan	Done
1) A user is logged into site and enters screening room from the purchase page	20-Jan	21-Jan	Done
2) A user has a ticket url but is not logged in; he should be able to click on the code, get taken to the lobby, enter a username. If no one is using the seat, he should be brought into the theater. If someone is already in the seat, that person should be sent a message asking if they want to let "username" take their seat. The second person's response determines if the new entrant gets in or not.	20-Jan	21-Jan	Done	Note, if a user's seat is taken, but then abandoned, that seat will be “orphaned”. So we need to think about seat abandonment.
3) A user who is not logged into the site is in the theater and goes from there to "Invite friends". Before they can do this they need to be prompted to log in or to create an account.	20-Jan	21-Jan	Done
4) Two users behind the same corporate firewall who want to use the same ticket link should still be subject to the lobby authentication check mechanism so they both can't be in the theater at the same time.	20-Jan	21-Jan	Done
Update Chat and Direct Chat to add “type”			Done

## Bugs
Item	Logged	Due Date	Status
Emails (tickets, recmmendations, etc) not reaching gmail	20-Jan	21-Jan	In Progress
Proper screening timing and countdown on Purchase Page; data seen above trailer does not correspond to the true timing of the screening	20-Jan	21-Jan
Fix the CSS in the Theater
Filter Screenings by Pay Status in Homepage
Do Host Video Streaming
Dismiss Theater Seat Requests
http://stage.constellation.tv/screening/VLpvBEhiBMQetTz	Side Image not correct for host